## Master Schedule
Order | Planned Date | Task Type | Phase | Section(s) | Task | Exercise | Related Result / Reason | Prerequisite | Proceed Gate | Actual Start | Actual End (exercise auto) | First-pass Status | Key Blocker | Suggested Redo Date (auto) | Actual Redo Date | Redo Result | Proceed? | Notes
1 | 2026-09-07 | Read | A. Meaning of weak convergence | 8.1 | Read the basic definitions. Separate vague, proper, weak, and complete convergence; mark exactly where continuity points of the limit df enter. |  |  | Start of Chapter 8 |  | 2026-09-07
2 | 2026-09-08 | Read | A. Meaning of weak convergence | 8.1 | Read Theorem 8.1.1, weak-limit uniqueness, and Examples 8.1.1–8.1.2. Make a one-page comparison: what converges, what does not, and why the limit must be proper. |  | Equivalence of the four definitions / uniqueness | 8.1 definitions read
3 | 2026-09-09 | Exercise | A. Meaning of weak convergence | 8.1 / Ch6 bridge | Do Exercise 2: rare spikes; compare convergence in probability, distribution, and almost sure convergence. | Ex 2 | 8.1 + Chapter 6 convergence hierarchy | 8.1 read
4 | 2026-09-10 | Exercise | A. Meaning of weak convergence | 8.1 / 8.2 | Do Exercise 4: discrete weak convergence, event indicators, point masses, and the mass-function caveat. Treat it as one multi-part exercise. | Ex 4 | Core mechanics of weak convergence; Scheffe bridge | Exercise 2 attempted
5 | 2026-09-11 | Exercise | A. Meaning of weak convergence | 8.1 / 8.5 | Do Exercise 10: construct weak convergence without convergence in probability. | Ex 10 | Why distributional convergence does not control the original coupling | Exercise 4 attempted
6 | 2026-09-12 | Exercise | A. Meaning of weak convergence | 8.1 | Do Exercise 18: give a discrete sequence converging weakly to a distribution with a density. | Ex 18 | Discrete-to-continuous weak convergence intuition | Exercise 10 attempted
7 | 2026-09-13 | Gate | A. Meaning of weak convergence | 8.1 | Proceed gate: explain, without formulas first, why convergence in distribution is a statement about laws rather than pointwise behavior of the original random variables; then state the continuity-point definition precisely. |  | Gate before Scheffe | Exercises 2, 4, 10, 18 attempted | Proceed only if you can distinguish weak convergence from a.s./i.p. convergence and explain the role of C(F).
8 | 2026-09-14 | Read | B. Scheffe and order statistics | 8.2 | Read Scheffe's lemma. Record both directions carefully: what density convergence is sufficient for, and what weak convergence does NOT imply about densities. |  | Total variation and L1 density distance | Block A gate passed
9 | 2026-09-15 | Read | B. Scheffe and order statistics | 8.2.1 | Read the order-statistics application. Focus on how density asymptotics plus Scheffe turn into convergence in distribution; keep the normalization visible. |  | Order statistics application of Scheffe | 8.2 read
10 | 2026-09-16 | Exercise | B. Scheffe and order statistics | 8.2 | Do Exercise 12: weak convergence to Uniform[0,1] while the densities fail to converge. | Ex 12 | Scheffe caveat / weak vs density convergence | 8.2 read
11 | 2026-09-17 | Exercise | B. Scheffe and order statistics | 8.2.1 | Do Exercise 8: exponential order statistics and the Gamma limit. | Ex 8 | Order statistics; direct method vs Renyi spacing representation | 8.2.1 read
12 | 2026-09-18 | Exercise | B. Scheffe and order statistics | 8.2.1 | Do Exercise 22: sample median / order-statistic limit using Scheffe's lemma. | Ex 22 | Scheffe + asymptotic order statistics | Exercise 8 attempted
13 | 2026-09-19 | Gate | B. Scheffe and order statistics | 8.2–8.2.1 | Proceed gate: distinguish weak convergence, total variation convergence, pointwise density convergence, and L1 density convergence. State exactly what Scheffe gives and what it does not give. |  | Gate before Skorohod / mapping | Block B exercises attempted | Proceed only if the implication arrows are explicit and you have one counterexample for a false converse.
14 | 2026-09-20 | Read | C. Skorohod, mapping, and delta | 8.3 | Read Proposition 8.3.1, Lemma 8.3.1, and the Baby Skorohod Theorem. Track the quantile construction and the crucial caveat: one-dimensional laws are matched, original dependence is not. |  | Baby Skorohod coupling / quantile map | Block B gate passed
15 | 2026-09-21 | Read | C. Skorohod, mapping, and delta | 8.3–8.3.1 | Read the Continuous Mapping Theorem and Delta Method. Separate the formal theorem from the intuition: continuity transfers the limit; the delta method is first-order linearization. |  | Continuous mapping + delta method | 8.3 read
16 | 2026-09-22 | Exercise | C. Skorohod, mapping, and delta | 8.3.1 | Do Exercise 1: binomial estimator and the log-odds transformation by the delta method. | Ex 1 | Delta method in statistical estimation | 8.3.1 read
17 | 2026-09-23 | Exercise | C. Skorohod, mapping, and delta | 8.3.1 | Do Exercise 7: transformed sample means; identify the derivative and limiting scale before calculating. | Ex 7 | Delta-method mechanics | Exercise 1 attempted
18 | 2026-09-24 | Exercise | C. Skorohod, mapping, and delta | 8.3 | Do Exercise 19: the second continuous mapping theorem. | Ex 19 | Mapping theorem with n-dependent maps | Exercise 7 attempted
19 | 2026-09-25 | Exercise | C. Skorohod, mapping, and delta | 8.3.1 / 8.6 | Do Exercise 23: multi-part delta-method and sample-variance problem. Protected deep exercise: if it needs more than one day, shift the schedule; do not start a new exercise in parallel. | Ex 23 | Delta method + sample variance + Slutsky-style reasoning | Exercise 19 attempted
20 | 2026-09-26 | Gate | C. Skorohod, mapping, and delta | 8.3–8.3.1 | Proceed gate: explain why Skorohod is a coupling device rather than a claim about the original variables, and reproduce the delta-method proof skeleton as 'linearization + negligible remainder + limit transfer'. |  | Gate before Portmanteau | Block C exercises attempted | Proceed only if the logical use of Skorohod/CMT is clear; do not memorize the coupling construction without its purpose.
21 | 2026-09-27 | Read | D. Portmanteau and the convergence map | 8.4 | Read the Portmanteau Theorem and its proof. Build a three-row equivalence table: df at continuity points, bounded continuous test functions, and continuity sets. |  | Portmanteau theorem | Block C gate passed
22 | 2026-09-28 | Read | D. Portmanteau and the convergence map | 8.5 | Read the relations among modes of convergence. Add Chapter 8 to your Chapter 6 convergence map, including the special constant-limit equivalence between i.p. and distribution. |  | a.s. => i.p. => distribution; constant-limit converse | 8.4 read
23 | 2026-09-29 | Exercise | D. Portmanteau and the convergence map | 8.4 | Do Exercise 5: monotone functions converging to a continuous limit; derive uniform convergence of cdfs when the weak limit is continuous. | Ex 5 | Continuity-point convergence strengthened by monotonicity | 8.4 read
24 | 2026-09-30 | Exercise | D. Portmanteau and the convergence map | 8.4 | Do Exercise 9: characterize weak convergence using continuous functions with compact support. | Ex 9 | Alternative Portmanteau test-function class | Exercise 5 attempted
25 | 2026-10-01 | Exercise | D. Portmanteau and the convergence map | 8.4 / Ch6 | Do Exercise 31: weak convergence plus a uniform moment bound; use Baby Skorohod and uniform integrability to recover moment convergence. | Ex 31 | Weak convergence + Chapter 6 UI | Exercise 9 attempted
26 | 2026-10-02 | Exercise | D. Portmanteau and the convergence map | 8.1 / 8.4 | Do Exercise 32: identify the Bernoulli weak limit from interior cdf convergence. | Ex 32 | Continuity-point logic when the limit has jumps | Exercise 31 attempted
27 | 2026-10-03 | Exercise | D. Portmanteau and the convergence map | 8.4 / 8.2 | Do Exercise 36: reweight probability measures by a continuous density g and prove weak convergence of the new measures. | Ex 36 | Portmanteau / Scheffe-style change of measure | Exercise 32 attempted
28 | 2026-10-04 | Gate | D. Portmanteau and the convergence map | 8.4–8.5 | Proceed gate: from a weak-convergence claim, choose the easiest of the three Portmanteau formulations and justify why it applies. Also reproduce the full convergence hierarchy from Chapter 6 through Chapter 8. |  | Gate before converging-together results | Block D exercises attempted | Proceed only if you can switch formulations deliberately rather than automatically using cdfs.
29 | 2026-10-05 | Read | E. Converging together and dependence | 8.6 | Read Slutsky's theorem and the Second Converging Together Theorem. Write the approximation template: tractable X_{u,n}, limit X_u, approximation error, then u -> infinity. |  | Slutsky / second converging-together theorem | Block D gate passed
30 | 2026-10-06 | Read | E. Converging together and dependence | 8.6.1 | Read the m-dependent CLT application. First pass goal: reproduce the variance calculation and the big-block/little-block architecture; do not get lost in block bookkeeping. |  | Hoeffding–Robbins m-dependent CLT / blocking | 8.6 read
31 | 2026-10-07 | Exercise | E. Converging together and dependence | 8.1 / 8.6 | Do Exercise 20: scaled geometric waiting time converges to a unit exponential. | Ex 20 | Direct distributional limit / scaling | 8.6 read
32 | 2026-10-08 | Exercise | E. Converging together and dependence | 8.1 / 8.6 | Do Exercise 21: first coincidence in sampling with replacement and its non-degenerate scaling limit. | Ex 21 | Distributional scaling / birthday-collision limit | Exercise 20 attempted
33 | 2026-10-09 | Exercise | E. Converging together and dependence | 8.6 / Ch9 bridge | Do Exercise 24: closure under convolution for normal, Poisson, and Cauchy types; decide what happens for the exponential type. | Ex 24 | Sums, types, and bridge to Chapter 9 characteristic functions | Exercise 21 attempted
34 | 2026-10-10 | Exercise | E. Converging together and dependence | 8.4 / CLT application | Do Exercise 14: a coordinate of the uniform distribution on the sphere converges to standard normal. | Ex 14 | High-dimensional normalization + weak convergence | Exercise 24 attempted
35 | 2026-10-11 | Gate | E. Converging together and dependence | 8.6–8.6.1 | Proceed gate: explain Slutsky as 'small perturbations do not change the weak limit' and explain the big-block/little-block proof as an approximation argument feeding the second converging-together theorem. |  | Gate before convergence to types | Block E exercises attempted | Proceed only if you can identify the approximating object and the error term in the m-dependent CLT.
36 | 2026-10-12 | Read | F. Convergence to types and extremes | 8.7 | Read the Convergence to Types Theorem. Focus on why two different normalizations of the same non-degenerate limit force the normalizing constants themselves to converge. |  | Convergence to Types Theorem | Block E gate passed
37 | 2026-10-13 | Read | F. Convergence to types and extremes | 8.7.1 | Read the extreme-value application. First pass: record the seven-step proof architecture and the three possible limit types; only deepen a functional-equation step if it blocks the architecture. |  | Extreme-value limit types | 8.7 read
38 | 2026-10-14 | Exercise | F. Convergence to types and extremes | 8.7 | Do Exercise 6: affine uniqueness for a non-degenerate distribution. This is the lemma used inside the convergence-to-types proof. | Ex 6 | Uniqueness of affine type parameters | 8.7 read
39 | 2026-10-15 | Exercise | F. Convergence to types and extremes | 8.7.1 | Do Exercise 17: normalize maxima of iid Uniform(0,1) variables and find a non-degenerate limit. | Ex 17 | Elementary extreme-value normalization | 8.7.1 read
40 | 2026-10-16 | Exercise | F. Convergence to types and extremes | 8.7.1 / Ch7 bridge | Do Exercise 16: regular variation criterion for Frechet-type maxima. Protected deep exercise; keep the Chapter 7 heavy-tail connection explicit. | Ex 16 | Regular variation / maxima / Chapter 7 heavy-tail bridge | Exercise 17 attempted
41 | 2026-10-17 | Exercise | F. Convergence to types and extremes | 8.7 | Do Exercise 26: symmetrize the normalized partial sums and use convergence to types. | Ex 26 | Convergence to types for sums; removal of centering | Exercise 16 attempted
42 | 2026-10-18 | Exercise | F. Convergence to types and extremes | 8.7.1 | Do Exercise 27: obtain a limit law for minima of iid non-negative variables from local density behavior. | Ex 27 | Extreme-value theory for minima | Exercise 26 attempted
43 | 2026-10-19 | Exercise | F. Convergence to types and extremes | 8.3.1 / 8.7.1 | Do Exercise 34: derive the Weibull-maximum weak limit from the exponential maximum using the delta method. | Ex 34 | Delta method + extremes | Exercise 27 attempted
44 | 2026-10-20 | Gate | F. Convergence to types and extremes | 8.7–8.7.1 | Proceed gate: state the convergence-to-types conclusion, explain what non-degeneracy prevents, and describe the three extreme-value types conceptually. Do not require yourself to reproduce every Hamel/Cauchy functional-equation detail before seeing the whole proof. |  | Gate before chapter summary | Block F exercises attempted | Proceed only if the theorem architecture is stable; unresolved technical substeps go to redo, not sideways expansion.
45 | 2026-10-21 | Summary | G. Chapter summary | Chapter 8 | Write the final Chapter 8 summary around: definitions, main results, proof ideas, technical tricks, pitfalls, and links to Chapters 6, 7, and 9. Make the convergence map the backbone. |  |  | All six block gates passed
46 | 2026-10-22 | Summary | G. Chapter summary | Chapter 8 | Final redo sweep: sort by Suggested Redo Date and resolve unfinished Totally ignorance / Spark / Skeleton rows. Only after this decide whether any optional exercise from the Exercise Map deserves promotion. |  |  | Chapter summary drafted

## Dashboard
Resnick Chapter 8 Schedule
Instruction: B3 records the baseline start date; Planned Date is a reference schedule, not a pace target. Fill Actual Start. For exercises, diagnose the first pass, then use the automatic redo date. Exercise Actual End is the actual redo date.
Plan start date (edit) | 2026-09-07
Total scheduled tasks | 46
Reading rows | 12
Exercise rows (core scheduled) | 26
Gate rows | 6
Summary rows | 2
Optional / unscheduled exercises | 10
Actual redo dates filled | 0
Redo due / unresolved | 0
Totally ignorance | 0
Spark | 0
Skeleton | 0
Crack it | 0
Main fill-out columns | K, M:N, P:Q, R:S in Master Schedule
Depth-control rule | Core schedule first; optional exercises are promoted only after a block gate or after the chapter summary.

## Redo Rules
First-pass Status | Meaning | Recommended Action | Redo Offset Days
Totally ignorance | Cannot write meaningful structure. | Redo next day after rereading the exact theorem/definition; ask for minimum hint only if still blank. | 1
Spark | Blur picture appears but needs ignition. | Redo after two days with one minimum hint. | 2
Skeleton | Direction is right but missing the logical bridge. | Redo after two days; focus only on the missing bridge. | 2
Crack it | Logic basically correct. | C1 after two days; no immediate full rewrite unless the proof was messy. | 2
Note | Actual Start is the first-attempt date. Suggested Redo Date = Actual Start + status offset. Exercise Actual End = Actual Redo Date.
Chapter 8 Depth-Control Rules
Core before optional | Complete the scheduled core exercise set before promoting Advanced/Optional items. | A Useful exercise may be promoted after its block gate if it tests a genuinely different idea.
Heavy exercise | Ex 4, 16, and 23 may legitimately take more than one day. | Freeze the schedule and continue the same exercise; do not open another exercise merely to keep the calendar moving.
Equivalence / alternate-proof trap | Do not expand one exercise into every possible direction by default. | After one correct proof and one genuinely illuminating alternative, ask whether another direction changes the chapter architecture. If not, park it.
Block gate | A gate checks architecture, not perfection. | Technical gaps become redo items; a gate should prevent details from erasing the big picture.
Final redo | Redo still matters even when the first proof was basically correct. | The goal is independent reproduction, not merely recognizing the book's argument.
Optional sweep | Optional exercises are not 'failed' or 'skipped'. | After the chapter summary, choose them only for a specific conceptual reason.
Minefield protocol | When an exercise is shared in chat, diagnose the user's literal idea first. | Identify the exact logical gap before giving hints; do not jump directly to a full solution.
Summary rule | Chapter summary is architectural reconstruction. | Organize it by definitions, main results, proof ideas, technical tricks, pitfalls, and connections.

## Exercise Map
Chapter 8 Exercise Map — all 36 exercises
Descriptions below are planning summaries, not replacements for the book's problem statements. Priority and scheduling are our study-plan judgments.
Exercise | Primary Tool / Section | Planning Summary | Role | Priority | Scheduled? | Suggested After | Depth Risk | Planning Note
1 | 8.3.1 Delta Method | Binomial estimator; delta method for log-odds | Core | Core | Yes | 8.3.1 | Normal | Statistical meaning + mechanics.
2 | 8.1 / 8.5 | Rare spikes; compare i.p., weak, and a.s. convergence | Core | Core | Yes | 8.1 | Normal | Excellent convergence-mode counterexample.
3 | 8.1 / Ch7–9 bridge | Products of uniforms; a.s. limit and centered/scaled weak limit | Extension | Useful | No | Block A or Chapter 9 | Normal | Good bridge, but not needed for the Chapter 8 backbone.
4 | 8.1 / 8.2 | Discrete weak convergence, Scheffe, events, point masses, mass-function caveat | Core | Core | Yes | 8.1 | Multi-part | Treat as one exercise; pause schedule if needed.
5 | 8.4 | Monotone functions and uniform cdf convergence with continuous limit | Core | Core | Yes | 8.4 | Normal | Strengthens continuity-point convergence.
6 | 8.7 | Affine uniqueness lemma for a non-degenerate df | Core | Core | Yes | 8.7 | Normal | A proof component of convergence to types.
7 | 8.3.1 | Delta-method transforms of sample means | Core | Core | Yes | 8.3.1 | Normal | Repetition is useful here because derivatives/scales should become automatic.
8 | 8.2.1 | Exponential order statistic -> Gamma limit | Core | Core | Yes | 8.2.1 | Normal | Compare brute-force and Renyi-spacing approaches.
9 | 8.4 | Compact-support test functions characterize weak convergence | Core | Core | Yes | 8.4 | Normal | Portmanteau refinement.
10 | 8.1 / 8.5 | Weak convergence without convergence in probability | Core | Core | Yes | 8.1 | Normal | Locks in the coupling distinction.
11 | 8.4 | Levy metric metrizes weak convergence | Theory Extension | Advanced/Optional | No | After Block D | High | Valuable topology, but can become a long technical detour.
12 | 8.2 | Weak convergence while densities do not converge | Core | Core | Yes | 8.2 | Normal | Direct warning against confusing weak and density convergence.
13 | 8.1 / 8.4 | Characterize weak convergence in normal / Poisson / exponential families | Extension | Useful | No | After Block D | Normal | Good parametric intuition; optional because the core map is already covered.
14 | 8.4 / CLT application | Coordinate of high-dimensional sphere -> standard normal | Application | Core | Yes | Block E | Normal | Beautiful application of normalization + weak convergence.
15 | 8.7 | Weissman extension of convergence-to-types | Theory Extension | Advanced/Optional | No | After Block F | High | Do only if you want more type-theorem structure.
16 | 8.7.1 / Ch7 bridge | Regular variation iff Frechet-type maxima; Cauchy/Pareto checks | Core Extension | Core | Yes | 8.7.1 | High | Protected deep exercise; strong bridge from Chapter 7 heavy tails.
17 | 8.7.1 | Uniform maxima under suitable normalization | Core | Core | Yes | 8.7.1 | Normal | Simplest hands-on extreme-value normalization.
18 | 8.1 | Discrete distributions converging to a continuous limit | Core | Core | Yes | 8.1 | Low | Quick intuition builder.
19 | 8.3 | Second continuous mapping theorem | Core | Core | Yes | 8.3 | Medium | Important for n-dependent transformations.
20 | 8.1 / 8.6 | Scaled geometric waiting time -> exponential | Application | Core | Yes | 8.6 | Normal | Clean distributional scaling example.
21 | 8.1 / 8.6 | First coincidence time / birthday scaling | Application | Core | Yes | 8.6 | Medium | Good nontrivial cdf limit.
22 | 8.2.1 | Sample median / order-statistic limit by Scheffe | Core | Core | Yes | 8.2.1 | Medium | Connects order statistics to asymptotic normality.
23 | 8.3.1 / 8.6 | Delta method plus sample variance, multiple parts | Core | Core | Yes | 8.3.1 | High | Protected deep exercise; do not split attention across other exercises.
24 | 8.6 / Ch9 bridge | Convolution closure of normal, Poisson, Cauchy types; exponential? | Bridge | Core | Yes | 8.6 | Medium | Sets up why transforms matter in Chapter 9.
25 | 8.4 / Ch9 bridge | Convolution transforms, smoothing, approximation, vague-limit examples | Theory Extension | Advanced/Optional | No | After Chapter Summary | Very High | Large multi-part problem; do only for a specific reason.
26 | 8.7 | Symmetrization and convergence to types for normalized sums | Core | Core | Yes | 8.7 | High | Deep but central use of the type theorem.
27 | 8.7.1 | Extreme-value limit for minima | Core Extension | Core | Yes | 8.7.1 | Medium | Complements maxima without adding a new theorem family.
28 | 8.1 / 8.2 | Oscillating dyadic densities; weak convergence to uniform | Extension | Useful | No | After Block B or D | Medium | A richer version of the density-convergence warning.
29 | 8.7 | Smooth normalizing functions in convergence to types | Theory Extension | Advanced/Optional | No | After Block F | High | Technical normalization theorem; not needed before summary.
30 | 8.7 / Ch6 | Replace arbitrary normalization by mean and sd under moment control | Theory Extension | Advanced/Optional | No | After Chapter Summary | High | Useful but proof can become moment/UI-heavy.
31 | 8.4 / Ch6 | Weak convergence + uniform moment control -> mean/variance convergence | Core | Core | Yes | 8.4 | Medium | Excellent Chapter 6 UI connection.
32 | 8.1 / 8.4 | Interior cdf convergence identifies Bernoulli limit | Core | Core | Yes | 8.4 | Normal | Forces careful handling of discontinuity points.
33 | 8.1 | Continuous df is uniformly continuous | Review | Useful | No | Any time | Low | Already appeared earlier in the book; use as review only if needed.
34 | 8.3.1 / 8.7.1 | Weibull maxima from exponential maxima via delta method | Core | Core | Yes | 8.7.1 | Medium | Connects two central Chapter 8 tools.
35 | 8.4 | Equicontinuous bounded test functions; convergence uniform in parameter | Theory Extension | Advanced/Optional | No | After Block D | High | Useful generalization, but not needed for the first pass.
36 | 8.4 / 8.2 | Continuous reweighting of measures preserves weak convergence | Core Extension | Core | Yes | 8.4 | Medium | Good synthesis of test functions and density ideas.