## Dashboard
Progress Dashboard
Metric | Value | Metric | Value
Start Date | see Protocol | Open C1 Reviews | 30
Total Units | 44 | Independent Reproductions | 0
Units Completed | 43 | Avg Read Min
Reading Units Done | 0 | Avg Ex Min | 172
Exercise Units Done | 30 | Daily Logs Filled | 6
Summary Units Done | 0 | Current Focus | See Unit Plan
Completion % | 97.73% | Last Completed Unit | See Unit Plan
Section Progress
Block | Planned Units | Completed | Notes
6.1–6.3 | 5 | 5 | Ground the convergence relations first
6.4–6.6 | 6 | 6 | Slow down at UI and L_p
Exercises | 13 | 13 | Use Reproduce level before marking complete

## Protocol
Chapter 6 Study Check-In Guide (A Probability Path) |  |  |  | Not Started | Not started
|  |  |  | Reading | My idea only
Start Date (edit) | 2026-04-02 | Status options | Reproduce level | Doing Exercises | Compared with answer
|  | Not Started |  | Completed | With help
Rules |  |  |  | Review | Independent
1. Track reading and exercises separately: use columns K–M for reading and N–P for exercises.
2. Actual start = when you begin the task; Actual end = when you truly finish that stage.
3. Exercise scheduling rule: plan at most one exercise problem per day.
4. For exercises, follow the protocol: write My idea first, then compare with the answer, then rewrite until independent.
5. C1 review is generated automatically as “exercise actual completion date + 2 days”.
6. Daily Log is for daily check-ins; Unit Plan is for tracking Chapter 6 by unit.
Suggested check-in order
First update status and times in Unit Plan, then add your daily reflection in Daily Log.
If a problem is not independently reproducible that day, keep Status as Doing Exercises and update Reproduce level to the current stage.
A Summary unit is complete when you can explain the core relationship map / counterexample bank in your own words.
Note on A1: Chapter 6 source file uploaded by user: /mnt/data/chap6.pdf
Note on B3: 可选：如果你想用 Suggested Day 自动生成建议日期，就在这里填本章开始日期。

## Unit Plan
Chapter 6 Study Check-in Plan
Start Date (linked) | edit in Protocol |  | Protocol | Read first, then do exercises; plan at most one exercise problem per day.
Unit ID | Suggested Seq | Type | Chapter Part | Topic / Task | Goal | Suggested Day | Suggested Date | Plan Read (min) | Plan Ex (min) | Read Start | Read End | Read Min | Ex Start | Ex End | Ex Min | Status | C1 Due | C1 Done? | Reproduce level | Notes | Link/Ref
R1 | 1 | Reading | 6.1 | Almost Sure Convergence | Definitions, exception set, a.s. equality, and limsup/liminf intuition | 1 | 2026-04-02 | 60 | [7 empty] | Completed |  | No
R2 | 2 | Reading | 6.2 | Convergence in Probability + 6.2.1 | Match a.s. vs i.p. with weak/strong consistency | 2 | 2026-04-03 | 60 | [7 empty] | Completed |  | No
R3 | 3 | Reading | 6.3(a) | Cauchy in Probability | Internalize the proof skeleton for “convergence in probability = Cauchy in probability” | 3 | 2026-04-04 | 75 | [7 empty] | Completed |  | No
R4 | 4 | Reading | 6.3(b) | Subsequence Criterion + Continuous Mapping | Internalize “every subsequence has an a.s.-convergent subsubsequence” | 4 | 2026-04-05 | 75 | [7 empty] | Completed |  | No
E01 | 5 | Exercise | Ex 1 | Exercise 1 — Core convergence 1 | Foundational problem on definitions and criteria | 5 | 2026-04-06 |  | 60 |  |  |  | 2026-04-06 10:00 | 2026-04-06 18:00 | 480 | Completed | 2026-04-08 | No
E12 | 6 | Exercise | Ex 12 | Exercise 12 — Core convergence 1 | Foundational problem on definitions and criteria | 6 | 2026-04-07 |  | 60 |  |  |  | 2026-04-07 13:00 | 2026-04-07 15:00 | 120 | Completed | 2026-04-09 | No
E17 | 7 | Exercise | Ex 17 | Exercise 17 — Core convergence 2 | Basic property: discrete case / event comparison / distance idea | 7 | 2026-04-08 |  | 50 | [6 empty] | Completed |  | No
E19 | 8 | Exercise | Ex 19 | Exercise 19 — Core convergence 2 | Basic property: discrete case / event comparison / distance idea | 8 | 2026-04-09 |  | 50 |  |  |  | 2026-04-09 14:00 | 2026-04-09 18:00 | 240 | Completed | 2026-04-11 | No
E21 | 9 | Exercise | Ex 21 | Exercise 21 — Core convergence 2 | Basic property: discrete case / event comparison / distance idea | 9 | 2026-04-10 |  | 50 | [6 empty] | Completed |  | No
E24 | 10 | Exercise | Ex 24 | Exercise 24 — Subsequence / mapping / metric | Apply the core ideas of Section 6.3 | 10 | 2026-04-11 |  | 60 |  |  |  | 2026-04-11 | 2026-04-11 | 0 | Completed | 2026-04-13 | No
E25 | 11 | Exercise | Ex 25 | Exercise 25 — Subsequence / mapping / metric | Apply the core ideas of Section 6.3 | 11 | 2026-04-12 |  | 60 |  |  |  | 2026-04-12 | 2026-04-14 | 2880 | Completed | 2026-04-16 | No
S1 | 12 | Summary | 6.1–6.3 | Summary Block 1 | Draw the relationship map: a.s. / i.p. / subsequence / continuous mapping | 12 | 2026-04-13 | 45 | [7 empty] | Completed |  | No
R5 | 13 | Reading | 6.4 | Quantile Estimation | Understand why quantile consistency is a natural application | 13 | 2026-04-14 | 50 | [7 empty] | Completed |  | No
R6 | 14 | Reading | 6.5 | L_p Convergence | Remember the definition, strength relations, and standard counterexamples | 14 | 2026-04-15 | 70 | [7 empty] | Completed |  | No
R7 | 15 | Reading | 6.5.1 | Uniform Integrability | First aim to use it: why UI is the bridge | 15 | 2026-04-16 | 80 | [7 empty] | Completed |  | No
R8 | 16 | Reading | 6.5.2 | Inequalities Review | How Schwarz / Hölder / Minkowski are used later | 16 | 2026-04-17 | 60 | [7 empty] | Completed |  | No
R9 | 17 | Reading | 6.6 (part 1) | More on L_p Convergence I | First master the L1 version and key lemma | 17 | 2026-04-18 | 80 | [7 empty] | Completed |  | No
R10 | 18 | Reading | 6.6 (part 2) | More on L_p Convergence II | Clarify the bridges among Lp-Cauchy, UI, and convergence in probability | 18 | 2026-04-19 | 80 | [7 empty] | Completed |  | No
E02 | 19 | Exercise | Ex 2 | Exercise 2 — Means and second moments | Connect convergence notions with averaging and L2 | 19 | 2026-04-20 |  | 60 |  |  |  | 2026-05-01 | 2026-05-01 | 0 | Completed | 2026-05-03 | No
E04 | 20 | Exercise | Ex 4 | Exercise 4 — Means and second moments | Connect convergence notions with averaging and L2 | 20 | 2026-04-21 |  | 60 |  |  |  | 2026-05-02 | 2026-05-02 | 0 | Completed | 2026-05-04 | No
E05 | 21 | Exercise | Ex 5 | Exercise 5 — UI basics | Basic UI practice: is a family uniformly integrable? | 21 | 2026-04-22 |  | 60 |  |  |  | 2026-05-03 | 2026-05-03 | 0 | Completed | 2026-05-05 | No
E06 | 22 | Exercise | Ex 6 | Exercise 6 — UI basics | Basic UI practice: is a family uniformly integrable? | 22 | 2026-04-23 |  | 60 |  |  |  | 2026-05-05 | 2026-05-05 | 0 | Completed | 2026-05-07 | No
E08 | 23 | Exercise | Ex 8 | Exercise 8 — UI basics | Basic UI practice: is a family uniformly integrable? | 23 | 2026-04-24 |  | 60 |  |  |  | 2026-05-06 | 2026-05-06 | 0 | Completed | 2026-05-08 | No
E03 | 24 | Exercise | Ex 3 | Exercise 3 — Inequalities + UI tests | Practice the estimation tools until fluent | 24 | 2026-04-25 |  | 70 |  |  |  | 2026-05-07 | 2026-05-07 | 0 | Completed | 2026-05-09 | No
E09 | 25 | Exercise | Ex 9 | Exercise 9 — Inequalities + UI tests | Practice the estimation tools until fluent | 25 | 2026-04-26 |  | 70 |  |  |  | 2026-05-08 | 2026-05-08 | 0 | Completed | 2026-05-10 | No
E10 | 26 | Exercise | Ex 10 | Exercise 10 — Inequalities + UI tests | Practice the estimation tools until fluent | 26 | 2026-04-27 |  | 70 |  |  |  | 2026-05-09 | 2026-05-09 | 0 | Completed | 2026-05-11 | No
E15 | 27 | Exercise | Ex 15 | Exercise 15 — L_p basics | See clearly what Lp, averaging, and scaling do and do not imply | 27 | 2026-04-28 |  | 70 |  |  |  | 2026-05-09 | 2026-05-09 | 0 | Completed | 2026-05-11 | No
E16 | 28 | Exercise | Ex 16 | Exercise 16 — L_p basics | See clearly what Lp, averaging, and scaling do and do not imply | 28 | 2026-04-29 |  | 70 |  |  |  | 2026-05-10 | 2026-05-10 | 0 | Completed | 2026-05-12 | No
E18 | 29 | Exercise | Ex 18 | Exercise 18 — L_p basics | See clearly what Lp, averaging, and scaling do and do not imply | 29 | 2026-04-30 |  | 70 |  |  |  | 2026-05-11 | 2026-05-11 | 0 | Completed | 2026-05-13 | No
E20 | 30 | Exercise | Ex 20 | Exercise 20 — Moment / tail / probability | Connect moment control with probability control | 30 | 2026-05-01 |  | 70 |  |  |  | 2026-05-12 | 2026-05-12 | 0 | Completed | 2026-05-14 | No
E22 | 31 | Exercise | Ex 22 | Exercise 22 — Moment / tail / probability | Connect moment control with probability control | 31 | 2026-05-02 |  | 70 |  |  |  | 2026-05-12 | 2026-05-12 | 0 | Completed | 2026-05-14 | No
E30 | 32 | Exercise | Ex 30 | Exercise 30 — Moment / tail / probability | Connect moment control with probability control | 32 | 2026-05-03 |  | 70 |  |  |  | 2026-05-12 | 2026-05-12 | 0 | Completed | 2026-05-14 | No
E11 | 33 | Exercise | Ex 11 | Exercise 11 — Maxima / extremes style | Tail behavior and extreme-value style probability estimates | 33 | 2026-05-04 |  | 70 |  |  |  | 2026-05-17 | 2026-05-17 | 0 | Completed | 2026-05-19 | No
E13 | 34 | Exercise | Ex 13 | Exercise 13 — Maxima / extremes style | Tail behavior and extreme-value style probability estimates | 34 | 2026-05-05 |  | 70 |  |  |  | 2026-05-18 | 2026-05-18 | 0 | Completed | 2026-05-20 | No
E14 | 35 | Exercise | Ex 14 | Exercise 14 — Maxima / extremes style | Tail behavior and extreme-value style probability estimates | 35 | 2026-05-06 |  | 70 |  |  |  | 2026-05-19 | 2026-05-19 | 0 | Completed | 2026-05-21 | No
E26 | 36 | Exercise | Ex 26 | Exercise 26 — Advanced L_p / UI examples | Counterexample bank plus structure problem | 36 | 2026-05-07 |  | 80 |  |  |  | 2026-05-20 | 2026-05-20 | 0 | Completed | 2026-05-22 | No
E27 | 37 | Exercise | Ex 27 | Exercise 27 — Advanced L_p / UI examples | Counterexample bank plus structure problem | 37 | 2026-05-08 |  | 80 |  |  |  | 2026-05-21 | 2026-05-21 | 0 | Completed | 2026-05-23 | No
E28 | 38 | Exercise | Ex 28 | Exercise 28 — Advanced L_p / UI examples | Counterexample bank plus structure problem | 38 | 2026-05-09 |  | 80 |  |  |  | 2026-05-22 | 2026-05-22 | 0 | Completed | 2026-05-24 | No
E23 | 39 | Exercise | Ex 23 | Exercise 23 — Mixed advanced | Constructed example / triangular-array / mixed-tool problem | 39 | 2026-05-10 |  | 80 |  |  |  | 2026-05-23 | 2026-05-23 | 0 | Completed | 2026-05-25 | No
E29 | 40 | Exercise | Ex 29 | Exercise 29 — Mixed advanced | Constructed example / triangular-array / mixed-tool problem | 40 | 2026-05-11 |  | 80 |  |  |  | 2026-05-25 | 2026-05-25 | 0 | Completed | 2026-05-27 | No
E33 | 41 | Exercise | Ex 33 | Exercise 33 — Mixed advanced | Constructed example / triangular-array / mixed-tool problem | 41 | 2026-05-12 |  | 80 |  |  |  | 2026-05-26 | 2026-05-26 | 0 | Completed | 2026-05-28 | No
E31 | 42 | Exercise | Ex 31 | Exercise 31 — Statistics-flavored | Connect median / central value with convergence notions | 42 | 2026-05-13 |  | 70 |  |  |  | 2026-05-27 | 2026-05-28 | 1440 | Completed | 2026-05-30 | No
E32 | 43 | Exercise | Ex 32 | Exercise 32 — Statistics-flavored | Connect median / central value with convergence notions | 43 | 2026-05-14 |  | 70 |  |  |  | 2026-05-29 | 2026-05-29 | 0 | Completed | 2026-05-31 | No
S2 | 44 | Summary | 6.4–6.6 | Summary Block 2 + Big Picture | Summarize the relationship map among L_p, UI, and moment convergence | 44 | 2026-05-15 | 50 | [7 empty] | Not Started |  | No
Formulas:
Suggested Date = IF(Protocol!$B3="","",Protocol!$B3+[Suggested Day]-1)
Note on A1: Built from the user's Chapter 6 PDF and the agreed study protocol. Source URL for Chapter 5 notes provided by user: https://archimondstat.github.io/resnick-notes/chap-5-integration-and-expectation.html

## Exercise Map
Exercise Map for Chapter 6
One exercise row = one problem. This matches the “max 1 problem per day” rule.
Unit ID | Exercises | Topic Cluster | Why this set matters | Priority | Suggested after | Done?
E01 | 1 | Core convergence 1 | Foundational problem on definitions and criteria | High | R4 | Yes
E12 | 12 | Core convergence 1 | Foundational problem on definitions and criteria | High | R4 | Yes
E17 | 17 | Core convergence 2 | Basic property: discrete case / event comparison / distance idea | High | R4 | Yes
E19 | 19 | Core convergence 2 | Basic property: discrete case / event comparison / distance idea | High | R4 | Yes
E21 | 21 | Core convergence 2 | Basic property: discrete case / event comparison / distance idea | High | R4 | No
E24 | 24 | Subsequence / mapping / metric | Apply the core ideas of Section 6.3 | High | R4 | No
E25 | 25 | Subsequence / mapping / metric | Apply the core ideas of Section 6.3 | High | R4 | No
E02 | 2 | Means and second moments | Connect convergence notions with averaging and L2 | Medium | R10 | No
E04 | 4 | Means and second moments | Connect convergence notions with averaging and L2 | Medium | R10 | No
E05 | 5 | UI basics | Basic UI practice: is a family uniformly integrable? | High | R10 | No
E06 | 6 | UI basics | Basic UI practice: is a family uniformly integrable? | High | R10 | No
E08 | 8 | UI basics | Basic UI practice: is a family uniformly integrable? | High | R10 | No
E03 | 3 | Inequalities + UI tests | Practice the estimation tools until fluent | Medium | R10 | No
E09 | 9 | Inequalities + UI tests | Practice the estimation tools until fluent | Medium | R10 | No
E10 | 10 | Inequalities + UI tests | Practice the estimation tools until fluent | Medium | R10 | No
E15 | 15 | L_p basics | See clearly what Lp, averaging, and scaling do and do not imply | High | R10 | No
E16 | 16 | L_p basics | See clearly what Lp, averaging, and scaling do and do not imply | High | R10 | No
E18 | 18 | L_p basics | See clearly what Lp, averaging, and scaling do and do not imply | High | R10 | No
E20 | 20 | Moment / tail / probability | Connect moment control with probability control | Medium | R10 | No
E22 | 22 | Moment / tail / probability | Connect moment control with probability control | Medium | R10 | No
E30 | 30 | Moment / tail / probability | Connect moment control with probability control | Medium | R10 | No
E11 | 11 | Maxima / extremes style | Tail behavior and extreme-value style probability estimates | Medium | R10 | No
E13 | 13 | Maxima / extremes style | Tail behavior and extreme-value style probability estimates | Medium | R10 | No
E14 | 14 | Maxima / extremes style | Tail behavior and extreme-value style probability estimates | Medium | R10 | No
E26 | 26 | Advanced L_p / UI examples | Counterexample bank plus structure problem | High | R10 | No
E27 | 27 | Advanced L_p / UI examples | Counterexample bank plus structure problem | High | R10 | No
E28 | 28 | Advanced L_p / UI examples | Counterexample bank plus structure problem | High | R10 | No
E23 | 23 | Mixed advanced | Constructed example / triangular-array / mixed-tool problem | Medium | R10 | No
E29 | 29 | Mixed advanced | Constructed example / triangular-array / mixed-tool problem | Medium | R10 | No
E33 | 33 | Mixed advanced | Constructed example / triangular-array / mixed-tool problem | Medium | R10 | No
E31 | 31 | Statistics-flavored | Connect median / central value with convergence notions | Medium | R10 | No
E32 | 32 | Statistics-flavored | Connect median / central value with convergence notions | Medium | R10 | No

## Daily Log
Daily Check-in Log
Use one row per day. This sheet is for reflections; Unit Plan remains the source of truth for timings.
Date | Day # | Units touched | Read min | Ex min | Actual total min | Big takeaway | Blocker | Next action | Mood / energy
2026-04-02 | 1
2026-04-03 | 2
2026-04-06 | 5
2026-04-07 | 6
2026-04-08 | 7
2026-04-09 | 8