## Master Schedule
Order | Planned Date | Task Type | Phase | Section(s) | Task | Exercise | Related Result / Reason | Prerequisite | Proceed Gate | Actual Start | Actual End (auto) | First-pass Status | Key Blocker | Suggested Redo Date (auto) | Actual Redo Date | Redo Result | Proceed? | Notes
1 | 2026-06-04 | Read | A. WLLN foundation | 7.1 | Read: truncation and tail equivalence. Make a one-page note: what changes after truncation and what remains equivalent. |  |  | Start of Chapter 7
2 | 2026-06-05 | Read | A. WLLN foundation | 7.2 | Read: General WLLN theorem. Write conditions (7.2)–(7.4) as a checklist: big jumps, truncated variance, centering. |  |  | 7.1 read
3 | 2026-06-06 | Exercise | A. WLLN foundation | 7.2 | Do Exercise 2: sample variance consistency. | 7.2 | 7.2 General WLLN / Chebyshev logic | Finish 7.1–7.2 reading
4 | 2026-06-07 | Exercise | A. WLLN foundation | 7.2 | Do Exercise 3: occupancy problem. | 7.3 | 7.2 WLLN / variance computation | Exercise 2 attempted
5 | 2026-06-08 | Exercise | A. WLLN foundation | 7.2 | Do Exercise 4: Monte Carlo integration interpretation. | 7.4 | 7.2 WLLN + Chapter 5 integration | Exercise 3 attempted
6 | 2026-06-09 | Exercise | A. WLLN applications | 7.2 | Do Exercise 21: exponential/gamma approximation using WLLN. | 7.21 | 7.2 WLLN | Exercise 4 attempted
7 | 2026-06-10 | Exercise | A. WLLN applications | 7.2 | Do Exercise 22: WLLN and inversion of Laplace transforms. | 7.22 | 7.2 WLLN | Exercise 21 attempted
8 | 2026-06-11 | Exercise | A. WLLN applications | 7.2 | Do Exercise 23: cube approximated by annulus. | 7.23 | 7.2 WLLN / iid uniform | Exercise 22 attempted
9 | 2026-06-12 | Exercise | A. WLLN applications | 7.2 | Do Exercise 27: further WLLN applications. | 7.27 | 7.2 WLLN | Exercise 23 attempted
10 | 2026-06-13 | Exercise | A. WLLN applications | 7.2 | Do Exercise 28: uncorrelated WLLN. | 7.28 | 7.2 WLLN / L2 convergence | Exercise 27 attempted
11 | 2026-06-14 | Gate | A. WLLN foundation | 7.1–7.2 | Proceed gate: can you state the WLLN checklist without looking? If not, redo reading notes before Block B. |  | Gate before 7.3 | Exercises 2,3,4,21,22,23,27,28 attempted | Proceed only if reading notes + at least first attempts are done
12 | 2026-06-15 | Read | B. a.s. convergence of sums | 7.3 | Read: Skorohod inequality, Kolmogorov convergence criterion, and tail/convergence logic. |  |  | Block A gate passed
13 | 2026-06-16 | Exercise | B. a.s. convergence of sums | 7.3 | Do Exercise 1: random signs and convergence of series. | 7.1 | 7.3 series convergence / later 7.6 check | 7.3 read
14 | 2026-06-17 | Exercise | B. a.s. convergence of sums | 7.3 | Do Exercise 5: L2 convergence and random signs. | 7.5 | 7.3 convergence criterion | Exercise 1 attempted
15 | 2026-06-18 | Exercise | B. a.s. convergence of sums | 7.3 | Do Exercise 7: partial converse to Borel-Cantelli. | 7.7 | 7.3 a.s. tools + Borel-Cantelli | Exercise 5 attempted
16 | 2026-06-19 | Exercise | B. a.s. convergence of sums | 7.3 | Do Exercise 34: normal sine series convergence. | 7.34 | 7.3 Kolmogorov convergence criterion | Exercise 7 attempted
17 | 2026-06-20 | Exercise | B. a.s. convergence of sums | 7.3 | Do Exercise 38: Cantor distribution series. | 7.38 | 7.3 almost sure convergence of series | Exercise 34 attempted
18 | 2026-06-21 | Exercise | B. a.s. convergence of sums | 7.3 | Do Exercise 41: bounded differences and variance condition. | 7.41 | 7.3 convergence criterion | Exercise 38 attempted
19 | 2026-06-22 | Exercise | B. a.s. convergence of sums | 7.3 | Do Exercise 42: convergence from summable variances. | 7.42 | 7.3 variance + Borel-Cantelli | Exercise 41 attempted
20 | 2026-06-23 | Gate | B. a.s. convergence of sums | 7.3 | Proceed gate: distinguish convergence of a series from convergence of averages. Record which theorem you used for each exercise. |  | Gate before SLLN | Block B exercises attempted | Proceed only if theorem usage is explicit
21 | 2026-06-24 | Read | C. SLLN mechanism | 7.4 | Read: Kronecker lemma and the strong law route from convergence of weighted series to normalized sums. |  |  | Block B gate passed
22 | 2026-06-25 | Read | C. SLLN mechanism | 7.4.1 | Read: two examples. Record how record counts and pure birth process use the preceding machinery. |  |  | 7.4 read
23 | 2026-06-26 | Exercise | C. SLLN mechanism | 7.4 | Do Exercise 18: stronger normalization with sqrt(n) log n. | 7.18 | 7.4 Kronecker / convergence criterion | 7.4 read
24 | 2026-06-27 | Exercise | C. SLLN mechanism | 7.4 | Do Exercise 31: Poisson sums normalized by expectation. | 7.31 | 7.4 SLLN for independent non-iid | Exercise 18 attempted
25 | 2026-06-28 | Exercise | C. SLLN mechanism | 7.4 | Do Exercise 32: max of exponentials over log n. | 7.32 | 7.4 examples + Borel-Cantelli | Exercise 31 attempted
26 | 2026-06-29 | Exercise | C. SLLN mechanism | 7.4 | Do Exercise 40: a.s. convergence criterion via probability and dyadic subsequence. | 7.40 | 7.4 a.s. vs i.p. bridge | Exercise 32 attempted
27 | 2026-06-30 | Gate | C. SLLN mechanism | 7.4 | Proceed gate: can you explain why Kronecker lemma is not just algebra but a device for SLLN? |  | Gate before iid SLLN | Block C exercises attempted | Proceed only if Kronecker role is clear
28 | 2026-07-01 | Read | D. iid SLLN and applications | 7.5 | Read: SLLN for iid sequences. Make an assumptions map: iid + integrability -> a.s. average convergence. |  |  | Block C gate passed
29 | 2026-07-02 | Read | D. iid SLLN and applications | 7.5.1 | Read: applications of SLLN. Separate 'proof pattern' from 'application interpretation'. |  |  | 7.5 read
30 | 2026-07-03 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 8: SLLN plus L1 convergence via uniform integrability. | 7.8 | 7.5 SLLN + Chapter 6 UI | 7.5–7.5.1 read or previous listed exercise attempted
31 | 2026-07-04 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 9: bounded coefficient weighted average. | 7.9 | 7.5 proof of SLLN | 7.5–7.5.1 read or previous listed exercise attempted
32 | 2026-07-05 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 10: m-dependent sequence and block frequencies. | 7.10 | 7.5 applications | 7.5–7.5.1 read or previous listed exercise attempted
33 | 2026-07-06 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 12: iterative uniforms and log limit. | 7.12 | 7.5 SLLN transformation | 7.5–7.5.1 read or previous listed exercise attempted
34 | 2026-07-07 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 16: maximum term over sum with nonzero mean. | 7.16 | 7.5 SLLN | 7.5–7.5.1 read or previous listed exercise attempted
35 | 2026-07-08 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 35: one-sided infinite mean and truncation. | 7.35 | 7.5 SLLN + truncation | 7.5–7.5.1 read or previous listed exercise attempted
36 | 2026-07-09 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 39: independent indicators WLLN. | 7.39 | 7.5 SLLN / WLLN | 7.5–7.5.1 read or previous listed exercise attempted
37 | 2026-07-10 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 43: Bernoulli expansion distributions and singularity. | 7.43 | 7.5 SLLN | 7.5–7.5.1 read or previous listed exercise attempted
38 | 2026-07-11 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 44: likelihood ratio product. | 7.44 | 7.5 SLLN on log likelihood ratio | 7.5–7.5.1 read or previous listed exercise attempted
39 | 2026-07-12 | Exercise | D. iid SLLN and applications | 7.5–7.5.1 | Do Exercise 45: entropy from matching probability. | 7.45 | 7.5 SLLN / information interpretation | 7.5–7.5.1 read or previous listed exercise attempted
40 | 2026-07-13 | Gate | D. iid SLLN and applications | 7.5–7.5.1 | Proceed gate: decide for each SLLN exercise whether it is direct SLLN, transformed SLLN, or truncation + SLLN. |  | Gate before three-series | Block D exercises attempted | Proceed only if each exercise has a theorem label
41 | 2026-07-14 | Read | E. Three-series theorem | 7.6 | Read: sufficiency of Kolmogorov three-series theorem. Make a three-column checklist: large jumps, variances, means. |  |  | Block D gate passed
42 | 2026-07-15 | Read | E. Three-series theorem | 7.6.1 | Read: necessity proof. Mark which direction uses tail equivalence and which uses convergence criterion. |  |  | 7.6 read
43 | 2026-07-16 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 6: gamma variables and a.s. convergence. | 7.6 | 7.6 three-series theorem | 7.6–7.6.1 read or previous listed exercise attempted
44 | 2026-07-17 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 11: symmetric iid harmonic series criterion. | 7.11 | 7.6 three-series / SLLN contrast | 7.6–7.6.1 read or previous listed exercise attempted
45 | 2026-07-18 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 13: exponential series conditions. | 7.13 | 7.6 three-series theorem | 7.6–7.6.1 read or previous listed exercise attempted
46 | 2026-07-19 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 14: normal series criterion. | 7.14 | 7.6 three-series / normal moments | 7.6–7.6.1 read or previous listed exercise attempted
47 | 2026-07-20 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 15: positive variables two-series reduction. | 7.15 | 7.6 positive version | 7.6–7.6.1 read or previous listed exercise attempted
48 | 2026-07-21 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 17: rare jumps and limiting partial sums. | 7.17 | 7.6 three-series / Borel-Cantelli | 7.6–7.6.1 read or previous listed exercise attempted
49 | 2026-07-22 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 19: nonnegative series equivalent conditions. | 7.19 | 7.6 positive series | 7.6–7.6.1 read or previous listed exercise attempted
50 | 2026-07-23 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 20: sufficient condition for a.s. convergence. | 7.20 | 7.6 three-series sufficient logic | 7.6–7.6.1 read or previous listed exercise attempted
51 | 2026-07-24 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 26: St. Petersburg a.s. limsup failure. | 7.26 | 7.6 / Borel-Cantelli | 7.6–7.6.1 read or previous listed exercise attempted
52 | 2026-07-25 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 33: necessary and sufficient exponent condition. | 7.33 | 7.6 three-series theorem | 7.6–7.6.1 read or previous listed exercise attempted
53 | 2026-07-26 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 36: positive series and expectations under tail condition. | 7.36 | 7.6 positive series | 7.6–7.6.1 read or previous listed exercise attempted
54 | 2026-07-27 | Exercise | E. Three-series theorem | 7.6–7.6.1 | Do Exercise 37: exponential series with only three-series theorem. | 7.37 | 7.6 three-series theorem | 7.6–7.6.1 read or previous listed exercise attempted
55 | 2026-07-28 | Gate | E. Three-series theorem | 7.6–7.6.1 | Proceed gate: for every series problem, record the three series explicitly or say why a simpler criterion applies. |  | Gate before advanced WLLN extras | Block E exercises attempted | Proceed only if three-series checklist is reproducible
56 | 2026-07-29 | Read | F. Advanced WLLN / heavy-tail extras | 7.2 + 7.6 review | Review: relative stability, triangular arrays, St. Petersburg, coupon collecting. This is a consolidation block, not new theorem reading. |  |  | Blocks A–E complete
57 | 2026-07-30 | Exercise | F. Advanced WLLN / heavy-tail extras | 7.2 / 7.6 / Ch8 bridge | Do Exercise 24: relative stability of sums and St. Petersburg paradox. | 7.24 | Advanced 7.2 WLLN / slowly varying functions | Main Chapter 7 machinery attempted
58 | 2026-07-31 | Exercise | F. Advanced WLLN / heavy-tail extras | 7.2 / 7.6 / Ch8 bridge | Do Exercise 25: triangular-array version of Theorem 7.2.1. | 7.25 | Advanced 7.2 WLLN | Main Chapter 7 machinery attempted
59 | 2026-08-01 | Exercise | F. Advanced WLLN / heavy-tail extras | 7.2 / 7.6 / Ch8 bridge | Do Exercise 29: heavy-tailed normalized lower limit. | 7.29 | Advanced WLLN / truncation | Main Chapter 7 machinery attempted
60 | 2026-08-02 | Exercise | F. Advanced WLLN / heavy-tail extras | 7.2 / 7.6 / Ch8 bridge | Do Exercise 30: classical coupon collecting. | 7.30 | WLLN with geometric variables | Main Chapter 7 machinery attempted
61 | 2026-08-03 | Exercise | F. Advanced WLLN / heavy-tail extras | 7.2 / 7.6 / Ch8 bridge | Do Exercise 46: Cauchy sums; mark as bridge to Chapter 8 if needed. | 7.46 | Chapter 7 + Chapter 8 bridge | Main Chapter 7 machinery attempted
62 | 2026-08-04 | Summary | G. Chapter summary | Chapter 7 | Write final Chapter 7 summary: definitions, main results, proof ideas, technical tricks, pitfalls, links to Chapter 6 and Chapter 8. |  |  | All exercise first attempts completed
63 | 2026-08-05 | Summary | G. Chapter summary | Chapter 7 | Final redo sweep: sort Master Schedule by Suggested Redo Date and complete unresolved Totally ignorance / Spark / Skeleton rows. |  |  | Chapter summary drafted

## Dashboard
Resnick Chapter 7 Schedule
Instruction | Fill Actual Start. For exercises, Suggested Redo Date is automatic. Fill Actual Redo Date when you actually redo; Actual End mirrors it.
Total tasks | 63
Reading rows | 10
Exercise rows | 46
Gate rows | 5
Summary rows | 2
Actual redo dates filled | 0
Redo due / unresolved | 0
Totally ignorance | 0
Spark | 0
Skeleton | 0
Crack it | 0
Main fill-out columns | K, M:N, P:Q, R:S in Master Schedule
Redo formula source | Actual Start + First-pass Status; Actual End = Actual Redo Date

## Redo Rules
First-pass Status | Meaning | Recommended Action | Redo Offset Days
Totally ignorance | Cannot write meaningful structure. | Redo next day after rereading the exact theorem/definition; ask for minimum hint only if still blank. | 1
Spark | Blur picture appears but needs ignition. | Redo after two days with one minimum hint. | 2
Skeleton | Direction is right but missing the logical bridge. | Redo after two days; focus only on the missing bridge. | 2
Crack it | Logic basically correct. | C1 after two days; no immediate redo unless proof was messy. | 2
Note | Actual Start is also the first attempt date for exercise rows. | Suggested Redo Date = Actual Start + offset. Actual End is automatically filled from Actual Redo Date.